## Gap Analysis
Area | Current state | Target state | Gap | Action | Priority | Owner | Deadline | Resources | Evidence / success criteria
Cybersecurity roles and responsibilities | No internal cybersecurity staff; responsibility falls on clinic owner and manager | Create a simple RACI assigning clinic owner, clinic manager, staff, and external IT provider responsibilities | The clinic lacks staff to contact in case of an IT security incident | Interview staff to define their current role and responsibility in terms of IT security. Create RACI. | 1 | Clinic manager and clinic owner | 1 month | RACI template, clinic leadership meeting, IT provider contract review. | Approved RACI table stored with clinic security documents
Legal, regulatory and contractual requirements | Staff receive HIPAA/privacy awareness training, but legal and vendor security requirements are not centrally documented or reviewed. | Maintain a simple register of legal, regulatory, and contractual cybersecurity/privacy requirements relevant to clinic operations, including HIPAA/privacy obligations, breach reporting expectations, and vendor security responsibilities. | The clinic lacks a centralized process for identifying and reviewing cybersecurity and privacy obligations and vendor responsibilities. | Create a requirements register covering patient privacy obligations, breach notification responsibilities, vendor security expectations, and backup/data protection requirements. | 3 | Clinic manager and clinic owner | 4 months | Vendor contracts, HIPAA/privacy guidance, IT provider input | Requirements register reviewed annually and after major vendor changes.
Inventory of hardware, software systems, and services | Asset inventory exists informally | Maintain a basic asset inventory reviewed quarterly and after device/software changes | Not all assets might be accounted for and the current scope of hardware, software, systems and services is in need of protection is unknown | Begin a formal asset inventory process by identifying and listing all existing hardware, software, systems and services | 2 | Clinic manager and IT provider | 3 months | Asset inventory spreadsheet or endpoint/device export. | Inventory contains all laptops/desktops, key software, cloud systems, owners, and review date
Data classification | Sensitive data is stored in known systems, but formal classification and handling guidance do not exist. | Document and classify patient, billing, staff, and operational data according to sensitivity and handling requirements. | Staff may not consistently understand how different categories of clinic data should be protected. | Create a simple data classification guide covering patient data, billing data, staff records, credentials, and general operational information. | 2 | Clinic manager and clinic owner | 2 months | Simple classification table/document, IT provider input | Data categories documented and shared with staff.
Risk register | No written threat documentation | Create a simple risk register covering ransomware, phishing, EHR outage, lost laptop, and third-party failure | Not all staff might be aware of the different possible threats and their consequences | Create a list of the most common threats with input from the IT provider and rank them according to their severity and how common they are | 2 | Clinic manager with input from IT provider and approval from clinic owner | 4 months | List of common cyber threats, IT provider input | Formal document of common threats and their indicators.
Third-party risk | The clinic relies heavily on third-party vendors, but cybersecurity responsibilities and escalation processes are not formally documented. | Identify critical third-party providers and document their cybersecurity responsibilities, contact information, and incident escalation procedures. | Vendor security expectations and incident responsibilities may be unclear during a disruption or security incident. | Review key vendors and document service responsibilities, security expectations, backup responsibilities, and incident contacts. | 1 | Clinic manager and clinic owner | 1 month | Vendor contracts, contact lists, IT provider support | Critical vendors documented with security contacts and responsibilities.
MFA | MFA for email but not billing | Enable MFA for email, EHR, billing, backup, and admin accounts; adopt password manager | MFA coverage is incomplete across critical accounts | Enable MFA for all key accounts and adopt password manager | 1 | IT provider | 1 month | Password manager subscription, Microsoft/Google MFA, EHR/billing MFA settings | MFA enabled for 100% of email, EHR, billing, backup, and admin accounts
Patching and updates | Systems are updated periodically by the IT provider, but patch status reporting and tracking are informal. | Ensure operating systems, software, and cloud services are updated regularly based on risk and vendor guidance. | The clinic lacks documented visibility into patch status and overdue updates. | Require the IT provider to implement a monthly patch review and provide patch status reporting for clinic systems. | 1 | IT provider | 1 month | Patch management reports, endpoint management tools | Monthly patch status review completed and documented.
Backup and restoration | Backups run but restore not tested | Define backup frequency, owner, retention, and test restoration quarterly | Clinic cannot confirm backups are usable during an incident | Define backup frequency, retention, owner, and quarterly restore test. | 2 | IT provider | 3 months | Existing backup platform, restore test checklist, IT provider support | Restore test completed and documented quarterly
Full-disk encryption | Acceptable use and device use policy. Staff use clinic-owned laptops/desktops | Enable full-disk encryption on clinic-owned laptops/desktops | Clinic -owned evices are not encrypted in case they are stolen or in the eventuality of a cyberattack | Enable full-disk encryption on all clinic-owned devices that currently lack it | 1 | IT provider | 1 month | IT provider support, encryption algorithm | Full-disk encryption enabled 100% on all clinic-owned devices.
Indicators of cybersecurity incidents | Staff receive general cybersecurity awareness training, but reporting procedures are informal. | Staff can identify and report common indicators of phishing, ransomware, unauthorized access, and suspicious system behavior. | Staff may not consistently recognize or report suspicious activity in a timely manner. | Create a simple suspicious activity reporting procedure and provide short phishing/ransom ware awareness refreshers. | 2 | Clinic manager and IT provider | 3 months | Awareness materials, reporting contact list, IT provider guidance | Staff know how to report suspicious emails, pop-ups, login activity, and device behavior.
External monitoring | External IT provider performs basic monitoring, but monitoring scope and escalation procedures are not formally documented. | Ensure critical systems and endpoints are monitored by the external IT provider and that security alerts are escalated appropriately. | Monitoring responsibilities and alert escalation processes may be inconsistent. | Define monitoring responsibilities, alert types, escalation contacts, and response expectations with the IT provider. | 1 | IT provider | 2 months | IT provider agreement, endpoint protection platform, monitoring documentation | Monitoring responsibilities documented and reviewed with the IT provider.
Incident response plan | No written IR plan | Create a one-page incident response plan with escalation, contacts, severity levels, and reporting steps | Staff may not know what to do during an incident | Create and approve a one- page incident response plan | 1 | Clinic manager and IT provider | 2 months | Incident response template, IT provider support, local CERT/CISA guidance if available | Plan approved, contact list complete, staff know reporting path
Recovery playbook | No formal playbook | Create recovery order: EHR, billing, email, appointment scheduling, file access, endpoints | The clinic would not know in which order to restore which services | Create and approve a list of services to be recovered and prioritize them | 3 | Clinic manager, clinic owner and IT provider | 4 months | Recovery playbook template, IT provider support, local CERT/CISA guidance if available | Recovery order documented and reviewed with IT provider